## Week1
Solutions | Task | Description | Type | Project / Prospect Client Name | Resources | Start Date | End Date | Estimated Hours | Status
MEANTest | MEANTest Approach for Angular 2 | Angular 2 IDE and workspace setup | Development - Enhancement | HONDA | Anup.NC | 2017-05-02 | 2017-05-02 |  | Completed
|  | Angular JS code analysis | Development - Enhancement | HONDA | Anup.NC | 2017-05-03 | 2017-05-03 |  | In progress
|  | Sample code generation | Development - Enhancement | HONDA | Anup.NC | 2017-05-04 | 2017-05-05 |  | On Hold
|  | TS to JS conversion | Development - Enhancement | HONDA | Anup.NC | 2017-05-04 | 2017-05-05 |  | In progress
MEANTest | MEANTest Approach for Angular 2 | Manual Execution of tscconfig.json through command prompt with project configurations | Development - Enhancement | HONDA | Akanksha Bhangare | 2017-05-02 | 2017-05-02 |  | Completed
| MEANTest Approach for Angular 2 | Rnd on tscconfig conflict with original tsc of corresponding project. | Development - Enhancement | HONDA | Akanksha Bhangare | 2017-05-03 | 2017-05-03 |  | Completed
| MEANTest Approach for Angular 2 | Sample code implementation to convert typeascript to javascript | Development - Enhancement | HONDA | Akanksha Bhangare | 2017-05-04 | 2017-05-05 |  | In progress
| Dice on Web | Setup and deployment of webservice war file. | Development - Enhancement | HONDA | Akanksha Bhangare | 2017-05-04 | 2017-05-05 |  | On Hold
| Dice on Web | Testing the entire setup as a whole for dice on web | Development - Enhancement | HONDA | Akanksha Bhangare | 2017-05-05 | 2017-05-05 |  | On Hold
DiCE | Client : FedEx Cross Border | Competitors : XPO Logistics, C H Robinson, PostNet | DiCE report | Adobe Summit | Sayali Dugane | 2017-05-02 | 2017-05-02 |  | Completed
| Client : Crowley | Competitors : APM Maersk, Mediterranean Shipping Company (MSC) | DiCE report | Crowley | Sayali Dugane | 2017-05-02 | 2017-05-02 |  | Completed
| Parse XML data into Database | Parse XML file nd try to import data in Mongodb | R&D | General | Sayali Dugane | 2017-05-03 | 2017-05-05 |  | In Progress
| PCB | Competitors : GENERAL MILLS, KELLOGG COMPAN, PEPSICO | DiCE report | PCB | Sayali Dugane | 2017-05-03 | 2017-05-04 |  | Completed
| IATrax product |  | DiCE report | IATrax product | Sayali Dugane | 2017-05-04 |  |  | In Progress
MUTE | Record screenshorts for reports | Python code to capture the user activity screenshot | Development | General | Karthikeyan | 2017-05-03 | 2017-05-05
| LTI Rebranding | Rebranding Demo | DEMO | General | Karthikeyan | 2017-05-04 | 2017-05-04
Web-CASA | X-Check Integration | To perform Cross-browser Testing with WebCASA using X-Check tool -- R&D on Testing with browsers' multiple versions. | R&D | General | Deepika Vaishnave | 2017-05-02 | 2017-05-05 |  | In Progress
Angular2 | Angular 2 testing | Gather angular 2 knowledge and spec creation . | R&D | Honda | Deepak Agarwal | 2017-05-02 | 2017-05-05 |  | In Progress
Angular2 | Angular 2 testing | Different type of services defination and their spec creation | R&D | Honda | Deepak Agarwal | 2017-05-03 | 2017-05-05 |  | In Progress
Angular2 | Angular 2 testing | Different type of directives defined and their spec creation | R&D | Honda | Deepak Agarwal | 2017-05-03 | 2017-05-05 |  | In Progress
Angular2 | Angular 2 testing | Different type of component defined and their spec creation | R&D | Honda | Deepak Agarwal | 2017-05-03 | 2017-05-05 |  | In Progress
Angular2 | Angular 2 | Mosaic training video on Angular 2 | Tutorial | Honda | Rahul kumar | 2017-05-02 | 2017-05-05 |  | In Progress
Angular2 | Angular 2 | Identify different types of specs in Angular2 | R&D | Honda | Rahul kumar | 2017-05-02 | 2017-05-05 |  | In Progress

## Week2
Solutions | Task | Description | Type | Project / Prospect Client Name | Resources | Start Date | End Date | Estimated Hours | Status
WebCASA | Cross Browser Testing R&D | found an open source project (BrowserShots) in Python, trying to understand- how to run | R&D | General | Deepika Vaishnave | 2017-05-08 | 2017-05-10 |  | in progress
| Machine Setup | Switch from 2GB to 8 GB RAM |  | General | Deepika Vaishnave | 2017-05-11 | 2017-05-11 |  | completed
| DICE Pdf report generation | forrester, nellsonhall, gartner,hfsresearch | Support | General | Deepika Vaishnave | 2017-05-11 | 2017-05-12 |  | completed
DiCE | Client : HFS | Competitors : Forrester, Gartner, NelsonHall | DiCE | Analyst | Sayali Dugane | 2017-05-08 | 2017-05-11 |  | completed
| Client : More Than | Competitors: Dirctline , Churchill | DiCE | RSA | Sayali Dugane | 2017-05-08 | 2017-05-08 |  | completed
| Client : DBS | Competitors : HSBC, SC | DiCE | DBS | Sayali Dugane | 2017-05-09 | 2017-05-09 |  | completed
| Client : Turner Bros | Competitors: CBS, CNN | DiCE | Turner Bros | Sayali Dugane | 2017-05-10 | 2017-05-10 |  | completed
| Client : Mandai | Competitors : Birdpark, Nparks, Blur Taronga | DiCE | Adobe Summit | Sayali Dugane | 2017-05-10 | 2017-05-10 |  | completed
| Client : Cigna | Competitors : United Health Group, Capital Blue. Blue of Calofornia | DiCE | Adobe Summit | Sayali Dugane | 2017-05-11 | 2017-05-11 |  | completed
| Client : Resmed | Competitors : Philips, Easy breathe | DiCE | Resmed | Sayali Dugane | 2017-05-12 |  |  | In progress
DiCE - MUTE | MUTE code Executable | To create a executable code for mute with libraries included. For Windows. | Development | General | Karthikeyan | 2017-05-08 | 2017-05-12 |  | Completed - Tested but need to integerate with GUI
| DEMO | DiCE DEMO | DEMO | RSA, Internal - Manoj | Karthikeyan | 2017-05-08 | 2017-05-12 |  | Completed
Angular 2 | Angular 2 | Angular 2 component sample code and specs | R&D | Honda | Deepak agarwal | 2017-05-08 | 2017-05-08 |  | In progress
| Setup and Demo | Setup, Demo ( manoj Khole ), Follow ups,solution to JCI issue. | Support |  | Deepak agarwal | 2017-05-10 | 2017-05-10 |  | Completed
| Meantest | Running of specs and lic setup | Implementation | Honda | Deepak agarwal | 2017-05-11 | 2017-05-11 |  | Completed
MEANTest | MEANTest Training | MEANTest demo training | Demo | Demo | Akanksha Bhangare | 2017-05-10 | 2017-05-10 |  | completed
| KT-Meantest flow | KT to rahul on MEANTest flow how it works ,How components are unterlinked and how to proceed with meantest 2 coding | Demo | HONDA | Akanksha Bhangare | 2017-05-08 | 2017-05-08 |  | completed
| Esprima setup code installation | Esprima setup code installation and integration with ts to js code | Implementation | HONDA | Akanksha Bhangare | 2017-05-09 | 2017-05-09 |  | completed
| MEANtest Execution issue | Code modification to solve meantest execution issue | Implementation | HONDA | Akanksha Bhangare | 2017-05-11 | 2017-05-11 |  | completed
| MEANTest setup and installation | MEANTest setup and installation on Jayesh's machine(HONDA) | Support | HONDA | Akanksha Bhangare | 2017-05-11 | 2017-05-11 |  | completed
| Guidance on XML traversal to rahul | Guidance on XML traversal to rahul | Support | HONDA | Akanksha Bhangare | 2017-05-12 | 2017-05-12 |  | In progress
Angular 2 | Mean test | Understanding Mean test flow code wise on angular 1 |  |  | Rahul kumar |  |  |  | In progress

## Week3
Solutions | Task | Description | Type | Project / Prospect Client Name | Resources | Start Date | End Date | Estimated Hours | Status
Web-CASA | Workflow Report generation : Instyle, People & Fortune | Workflow Code Correction while generating reports | Bug Fixing |  | Deepika Vaishnave | 2017-05-15 | 2017-05-16 | 18 | completed
| Instyle Dice Report generation | Competitors: Elle & harperBazaar | Reporting |  | Deepika Vaishnave | 2017-05-17 | 2017-05-17 | 9 | completed
| Xml To Json Conversion | Xml To Json Conversion For MongoDB | Development - Enhancement |  | Deepika Vaishnave | 2017-05-18 | 2017-05-19 |  | in progress
MEANTest | Analysis of code samples & Parsing logic | Analysis of code samples(Components and services) to formulate the parsing logic | Rnd | HONDA | Akanksha Bhangare | 2017-05-15 | 2017-05-15 |  | completed
| Splitting code parts and Parsing logic | Component and service code-break-up for parsing logic(identifying the code parts to be parsed & rough parsing logic for the same) | Rnd | HONDA | Akanksha Bhangare | 2017-05-15 | 2017-05-15 |  | completed
| Implementation of backbone code structure for parsing | Implementation of backbone code structure to traverse all xmls recursively and parse the unit type(Component/service) and fetch it's name.(Collective work with Akhil and Rahul) | Support | HONDA | Akanksha Bhangare | 2017-05-16 | 2017-05-17 |  | completed
| Implementation of backbone code structure for spec generation. | Implementation of backbone code structure to generate basic spec files using template with component/service name injected in it.(Collective work with Akhil and Rahul) | Support | HONDA | Akanksha Bhangare | 2017-05-17 | 2017-05-17 |  | completed
| Guidance and rnd on parsing logic for import definitions. | Rnd on parsing logic for import definitions with Akhil and Deepak. | Support | HONDA | Akanksha Bhangare | 2017-05-18 | 2017-05-18 |  | completed
| Implementation for fetching import definitions | Implementation for fetching import definitions | Support | HONDA | Akanksha Bhangare | 2017-05-19 | 2017-05-19 |  | In progress
| Implementation of backbone code structure for parsing | Implementation of backbone code structure to traverse all xmls recursively and parse the unit type(Component/service) and fetch it's name.(Collective work with Akhil and Akanksha) | Support | HONDA | Rahul kumar | 2017-05-16 | 2017-05-17 |  | completed
| Implementation of backbone code structure for spec generation. | Implementation of backbone code structure to generate basic spec files using template with component/service name injected in it.(Collective work with Akhil and Akanksha) | Support | HONDA | Rahul kumar | 2017-05-17 | 2017-05-17 |  | completed
Meeting Demos & Discussion | Part of Multiple Demos and discussion | HFS( london),Gatner,Nellson hall( Paris),Resmed | Demo | Analyst | Deepak Agarwal | 2017-05-15 | 2017-05-18 |  | Completed
| Cordinated with HBOnet for Webcasa Setup | Setup and expalining tool webcasa to Zeeshan Khalife | Support | HBO | Deepak Agarwal | 2017-05-15 | 2017-05-18 |  | In-progress
| Dice | Time Inc. ( Workflow , Dice ) , Munic Re,Reliant | Support | Time Inc,Munic Re,Resmed | Deepak Agarwal | 2017-05-15 | 2017-05-18 |  | Completed
| ESDS machine Follow up | IT and ESDS resprentative coordination | Co-ordination | Cloud machine | Deepak Agarwal | 2017-05-15 | 2017-05-18 |  | In-progress
| Discussion | Meeting with Anand Iyer w.r.t Digital Assurance services/Tools | Discussion | Internal meeting with Sales | Deepak Agarwal | 2017-05-15 | 2017-05-18 |  | Completed
MeanTest2 | Following up with team to understand the progress and part of creating logic to identify Imports in Angualr 2 (both services and component ) | Parsing logic brainstoming for Imports | Rnd | HONDA | Deepak Agarwal | 2017-05-18 | 2017-05-19 |  | In-progress
MeanTest2 | Implementation of backbone code structure for parsing | Implementation of backbone code structure to traverse all xmls recursively and parse the unit type(Component/service) and fetch it's name.(Collective work with Rahul and Akanksha) | Rnd | HONDA | Akhil Cherian | 2017-05-16 | 2017-05-17 |  | completed
| Implementation of backbone code structure for spec generation. | Implementation of backbone code structure to generate basic spec files using template with component/service name injected in it.(Collective work with Rahul and Akanksha) | Development | HONDA | Akhil Cherian | 2017-05-17 | 2017-05-17 |  | completed

## Week4
Solutions | Task | Description | Status | Type | Project / Prospect Client Name | Resources | Start Date | End Date | Estimated Hours
Web-CASA | MongoDB | Creating a central repository for DiCE | In Progress | Development - Enhancement | General
|  | Automating Spider Chart | In Progress | Development - Enhancement | General
MeanTest2 | Component with function related samples | To find different ways to defining a component( component with methods and conditional statements) | Completed | Development | Honda
| Services with function related samples | To find different ways to defining a Services( Services with methods and conditional statements) | Completed | Development | Honda
| If & Else | If & else logic with extraction from XMl and writing it in Spec file | Completed | Development | Honda
| TestBed : Component | To identify Component TestBed Configuration and create a general Template in code to be used while spec file generation | Completed | Development | Honda
| TestBed : Service | To identify Service TestBed Configuration and create a general Template in code to be used while spec file generation | Completed | Development | Honda
| Fetching Method's Names And Body | Traverse all xmls recursively and parse the method and fetch it's name and its body | Completed | Development | Honda
| Fetching method parameters and mapping with exciting code | Data structure to map fetched method with its method body & and fetch it's param | Completed | Development | Honda
| Writing imports in spec file | Implementation of code for writing imports in spec file with respect to project structure | Completed | Development | Honda
| Code for parsing of variables in methods | Code Implementation for identifying and creating a list of requried variables and filtering it from the method list. | Completed | Development | Honda
| Code integration | Combined all the code with Ts to XML with Parsing and spec generation. | Completed | Development | Honda
|  | Code implementation for ifconditions with escodegen setup | Completed | Development | Honda
| Service Name extraction used inside component | To identify different Service used inside a component and extract its name to help finiding variable names inside each method | In Progress | Development | Honda
| Variables Filter with services used inside component | To identify different Service used inside a component and extract its name to help finiding variable names inside each method | In Progress | Development | Honda
| Spec File Creation | Generate File using Code with new template defined ( inculdes TestBed,Var & IF/else ). | In Progress | Development | Honda
| Manual Spec Creation | To write manual spec for sample application to find out gaps and error . | In Progress | Development | Honda
DiCE Report | Chevron | Competitors: Exxon, Conocophillips | Completed | DiCE report creation | CHV ABU visit
| More Than | Competitors: Dirctline , Churchill | Completed | DiCE report creation | RSA
| Apollo Munich | Competitors: Max Bupa, Star Health | Completed | DiCE report creation | Apollo Munich RFP
| Munich RE | Competitors: Swiss RE, Hannover RE | Completed | DiCE report creation | Munich RE
| Veolia | Competitors: ENGIE COFELY, VINCI | In Progress | DiCE report creation | Veolia
| BAGIC | Competitors: TATA AIG, ICICI Lombard, HDFC Ergo | In Progress | DiCE report creation | BAGIC
| tryg.com | yet to receive |  | DiCE report creation | tryg
| Standard Chatered | Competitors:SCB Singapore, SCB Hong Kong | In Progress | DiCE report creation | Standard chatered
| Standard Chatered india | Competitors:ABN AMRO ,Barclays Bank | In Progress | DiCE report creation | Standard chatered
DiCE - MUTE | DiCE Demo | Gatner, Chevron:Detail demo on DiCE Implementation | Completed | DEMO | Gatner, Chevron
| MUTE Executable - Windows & MAC | Create a executable code for MUTE on windows and Mac | Completed for windows | Development - Enhancement | General
| MUTE Execution - S2 | Setting up the DiCE Perception for Citi and generate reports on perception | In progress | Support | Citi
| MUTE Report | Analysing the report for perception range and format | In progress | Analysis | General

## Week5
Solutions | Task | Description | Status | Type | Project / Prospect Client Name | Resources | Start Date | End Date | Estimated Hours
WebCASA | Mongo DB | Json Creation From Web-CASA | Completed | Development /Enhancement | General
MeanTest2 | Executing manually written code and analyzing the gaps in our Template | Importing the project into workspace and manually executing spec to discover the gaps in auto generated specs | Completed | Analysis | Honda
| Component spec writing | Code to write down specs for component | Completed | Development | Honda
| Code gap fixing | Code fixes for spec generation ( parameters repeated fix , Import missing fixed,testbed Async added, default it blocks added ). | Completed | Development | Honda
| Variables with "let" keyword | Fetching Method Variables with "let" keyword to be written in spec generation | Completed | Development | Honda
| code coverage of the auto generated spec | Code coverage of auto generated spec with ill updates made manually | In progress | Analysis | Honda
DiCE Report | BAGIC DiCE Report | BAGIC Manual Report Generation | Completed | DiCE | General
| tryg.com | Competitors : Topdanmark, Codan | Completed | DiCE report creation | tryg
| Standard Chatered | Competitors:SCB Singapore, SCB Hong Kong | Completed | DiCE report creation | Standard chatered
| Standard Chatered India | Competitors:ABN AMRO ,Barclays Bank | Completed | DiCE report creation | Standard chatered
DiCE - MUTE | DiCE Demo | Detail demo on DiCE Implementation | Completed | DEMO | SCB
| MUTE Executable - MAC | Create a executable code for MUTE on Mac | In Progress | Development | General
| MUTE Execution - S2 | Setting up the DiCE Perception for Citi and generate reports on perception | In progress | Support | Citi
| MUTE Report | Analyzing the report for perception range and format | In progress | Analysis | General
DiCE Development | Mongo DB | Json to Mongo DB | Completed | Development /Enhancement | General
| Mongo DB | Creation of DiCE Spider chart ,Adding formulas to Mongo DB for Spider chart creation | In Progress | Development /Enhancement | General
| Visitors parameters | to Add New Visitors parameters in WebCASA | In Progress | Development /Enhancement | General

## Sheet1
Deepika vaishnave | Analysis
Sayali Dugane | Bug Fixing
Karthikeyan Balasubramanian | Development - Enhancement
Akanksha Bhangare | Development -New Functionality
Testing
Support
Documentation
Training
Demo
KT